## Cover Page
Smart_Shop
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Project ID: Car Servicing | <HYD19IJ003/20> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Smart Shop Project ID: <HYD19IJ003/20> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1 | 1 | Ability of the system to procure the fundamental details of the user |  | 0.5 | 0.5 | [5 empty] | Completed
FEA 2 | 2 | Ability of the system to authenticate the user credentials of the registered user |  | 0.5 | 0.5 | [5 empty] | Completed
FEA 3 | 3 | Ability of the system to display the current stock products to the user based on the input given by the user and also show the location of the product in the shop |  | 0.6 |  | 0.6 |  |  |  |  | Completed
FEA 4 | 4 | Ability of the system to procure the fundamental details of the Shop Manager |  | 0.4 |  | 0.4 |  |  |  |  | Completed
FEA 5 | 5 | Ability of the system to authenticate the user credentials of the registered Shop manager |  | 0.6 |  |  | 0.6 |  |  |  | Completed
FEA 6 | 6 | Ability of the system to allow the shop manager to add/modify the stock inventory of the Shop |  | 0.7 |  |  | 0.4 | 0.3 |  |  | Completed
FEA 7 | 7 | Ability of the system to allow the Shop manager to add the Product details |  | 0.5 |  |  |  | 0.5 |  |  | Completed
FEA 8 | 8 | Ability of the system to allow the Shop manager to generate bill for the selected products of the customer. |  | 0.8 |  |  |  | 0.4 | 0.4 |  | Completed
FEA 9 | 9 | Ability of the system to update the stock once the item is billed. (The count of the quantity billed will be deducted from the total stock) |  | 0.4 |  |  |  |  | 0.4 |  | Completed
FEA 10 | 10 | Ability of the system to update the Purchase history once billing is done for the customer. |  | 0.5 |  |  |  |  | 0.2 | 0.3 | Completed
FEA 11 | 11 | Ability of the system to allow the Shop manager to update the aisle and shelf details |  | 0.3 | [5 empty] | 0.3 | Completed
FEA 19 | 12 | Ability of the system to disconnect from the system on clicking Log off. |  | 0.2 | [5 empty] | 0.2 | Completed
|  | Total |  | 6 | 1 | 1 | 1 | 1.2 | 1 | 0.8
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A